## Personas
Persona Type | Skill Level | Standard Days/Week | Notes
Infrastructure Architect | Senior | 5 | Part-time (2.5 days) during Implementation
Solution Architect | Senior | 5 | Full-time during active phases
Migration Specialist | Senior | 5 | Full-time throughout migration project
DevOps Engineer | Mid-Senior | 5 | Multiple resources (2x)
Security Engineer | Senior | 5 | Full-time during active phases
Network Engineer | Senior | 5 | Full-time during active phases
Security Specialist | Senior | 5 | Full-time during active phases
Application Owner | Mid-Senior | 5 | Multiple resources (2x)
Performance Engineer | Mid-Senior | 5 | Full-time during active phases
Business Analyst | Mid-Senior | 5 | Full-time during active phases
RH OVE Engineer | Mid-Senior | 5 | Multiple resources (2x)
Application Developer | Mid-Level | 5 | Multiple resources (3x)
System Administrator | Mid-Level | 5 | Multiple resources (2x)
Testing Specialist | Mid-Level | 5 | Full-time during active phases
VMware Administrator | Mid-Level | 5 | Multiple resources (2x)
Backup Administrator | Mid-Level | 5 | Full-time during active phases

## Infrastructure Weekly
Week | Phase | Infrastructure Architect | DevOps Engineer (2x) | System Administrator (2x) | Security Engineer | Network Engineer | Weekly Total (Days)
1-4 | Study | 5 | 0 | 0 | 0 | 5 | 10
5-12 | Design | 5 | 10 | 0 | 5 | 5 | 25
13-20 | Implementation | 2.5 | 10 | 10 | 5 | 5 | 32.5
21-24 | Testing | 0 | 10 | 10 | 5 | 0 | 25
25-28 | Day-2 Ops | 0 | 10 | 10 | 0 | 0 | 20

## Infrastructure Phases
Phase | Weeks | Person-Days
Study Phase | 1-4 | 40
Design Phase | 5-12 | 200
Implementation Phase | 13-20 | 260
Testing Phase | 21-24 | 100
Day-2 Operations | 25-28 | 80
TOTAL |  | 680

## Use-Cases Weekly
Week | Phase | Solution Architect | Application Developer (3x) | Testing Specialist | DevOps Engineer | Security Specialist | Business Analyst | Weekly Total (Days)
15-18 | Study | 5 | 0 | 0 | 0 | 0 | 5 | 10
19-26 | Design | 5 | 0 | 0 | 0 | 5 | 5 | 15
27-38 | Implementation | 0 | 15 | 0 | 5 | 5 | 0 | 25
39-42 | Testing | 0 | 15 | 5 | 5 | 5 | 0 | 30
43-46 | Day-2 Ops | 0 | 0 | 0 | 5 | 0 | 0 | 5

## Use-Cases Phases
Phase | Weeks | Person-Days
Study Phase | 15-18 | 40
Design Phase | 19-26 | 120
Implementation Phase | 27-38 | 300
Testing Phase | 39-42 | 120
Day-2 Operations | 43-46 | 20
TOTAL |  | 600

## Migration Weekly
Week | Phase | Migration Specialist | VMware Admin (2x) | RH OVE Engineer (2x) | Application Owner (2x) | Performance Engineer | Backup Administrator | Weekly Total (Days)
21-28 | Study | 5 | 10 | 0 | 0 | 0 | 0 | 15
29-36 | Design | 5 | 10 | 0 | 10 | 0 | 0 | 25
37-50 | Implementation | 5 | 10 | 10 | 10 | 5 | 5 | 45
51-54 | Testing | 5 | 0 | 10 | 10 | 5 | 5 | 35
55-60 | Day-2 Ops | 5 | 0 | 10 | 0 | 5 | 5 | 25

## Migration Phases
Phase | Weeks | Person-Days
Study Phase | 21-28 | 120
Design Phase | 29-36 | 200
Implementation Phase | 37-50 | 630
Testing Phase | 51-54 | 140
Day-2 Operations | 55-60 | 150
TOTAL |  | 1240

## Project Summary
Sub-Project | Duration (Weeks) | Total Workload (Person-Days) | Average Weekly Workload (Days)
RH OVE Infrastructure | 28 | 582.5 | 20.8
Use-Cases Implementation | 32 | 560 | 17.5
Migration from VMware | 40 | 869 | 21.7
TOTAL | 100 | 2011.5 | 60

## Peak Utilization
Week Range | Projects Active | Weekly Workload (Days) | Key Activities
37-42 | Infrastructure + Use-Cases + Migration | 102.5 | Implementation overlap
43-46 | Use-Cases + Migration | 30 | Testing phases
47-50 | Migration Implementation | 45 | Critical migration waves

## Workload Distribution
Persona Type | Total Weeks Active | Total Workload (Days) | Percentage
Migration Specialist | 40 | 200 | 9.9
Application Developer (3x) | 16 | 240 | 11.9
RH OVE Engineer (2x) | 24 | 240 | 11.9
VMware Administrator (2x) | 28 | 280 | 13.9
DevOps Engineer (2x) | 36 | 360 | 17.9
Infrastructure Architect | 18.5 | 92.5 | 4.6
System Administrator (2x) | 16 | 160 | 8
Security Engineer | 16 | 80 | 4
Network Engineer | 20 | 100 | 5
Solution Architect | 12 | 60 | 3
Testing Specialist | 4 | 20 | 1
Security Specialist | 12 | 60 | 3
Business Analyst | 4 | 20 | 1
Application Owner (2x) | 26 | 260 | 12.9
Performance Engineer | 18 | 90 | 4.5
Backup Administrator | 30 | 150 | 7.5